## Summary
AIMarketPlace | Software Project Report
Project Name | AIMarketPlace — AI Tools & Freelance Gig Marketplace Platform
Report Type | Work Breakdown Structure (Epic → Feature → Story → Task)
Prepared By | Program Management Office
Report Date | 2026-07-16
Project Start | 04-0-7-2026
Projected Completion | 2026-07-24
Total Epics | 11
Total Features | 20
Total Stories | 37
Total Tasks | 84
Project Description
AIMarketPlace is a two-sided web platform connecting businesses (Company accounts) that need AI tools/services with independent developers (Freelancer accounts) who deliver them, alongside a public marketplace for discovery and comparison of AI tools and vendors. The platform is built on React 19, TypeScript and Vite, with Redux Toolkit and TanStack Query for state management, Radix UI and Tailwind for the design system, and role-based workspaces for Guest, Company (CRM), Developer (Freelancer) and Admin users.
Assignee Employee ID Legend
Employee ID | Role
100298 | Software Engineer
Priority Legend
High | Core platform functionality — blocking dependency for downstream work
Medium | Important functionality — required for release but not a hard blocker
Low | Enhancement / supporting content — schedule around higher-priority work

## WBS
Project code | Project Name | Epic Code | Epic Name | Feature | Story | Task | Priority | Start Date | Due Date | Assignee Employee ID
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0001 | Platform Architecture & Foundation | Project Scaffolding & Build Tooling | Initialize Vite + React + TypeScript workspace | Configure Vite build pipeline & path aliases | High | 2026-04-06 | 2026-04-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0002 | Platform Architecture & Foundation | Project Scaffolding & Build Tooling | Initialize Vite + React + TypeScript workspace | Configure TypeScript strict compiler options | High | 2026-04-09 | 2026-04-10 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0003 | Platform Architecture & Foundation | Project Scaffolding & Build Tooling | Initialize Vite + React + TypeScript workspace | Set up Oxlint rules & CI lint gate | Medium | 2026-04-06 | 2026-04-07 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0004 | Platform Architecture & Foundation | Project Scaffolding & Build Tooling | Application state & data layer setup | Configure Redux Toolkit store & slices | High | 2026-04-08 | 2026-04-10 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0005 | Platform Architecture & Foundation | Project Scaffolding & Build Tooling | Application state & data layer setup | Integrate TanStack React Query for server state | High | 2026-04-13 | 2026-04-15 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0006 | Platform Architecture & Foundation | Project Scaffolding & Build Tooling | Application state & data layer setup | Build Axios API service layer & interceptors | High | 2026-04-06 | 2026-04-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0007 | Platform Architecture & Foundation | Design System & Theming | Core UI component library | Build GlassCard, Badge, StatCard primitives | Medium | 2026-04-06 | 2026-04-09 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0008 | Platform Architecture & Foundation | Design System & Theming | Core UI component library | Integrate Radix UI primitives (Dialog, Dropdown, Tabs, Tooltip) | Medium | 2026-04-10 | 2026-04-15 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0009 | Platform Architecture & Foundation | Design System & Theming | Core UI component library | Establish Tailwind + class-variance-authority styling conventions | Medium | 2026-04-06 | 2026-04-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0010 | Platform Architecture & Foundation | Design System & Theming | CRM theme engine | Build ThemeContext & useCrmTheme hook | Medium | 2026-04-06 | 2026-04-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0011 | Platform Architecture & Foundation | Design System & Theming | CRM theme engine | Build Theme Settings page for tenant branding | Low | 2026-04-09 | 2026-04-13 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0012 | Authentication & Role-Based Access Control | Authentication Flows | Login experience | Build Login page UI & auth visual panel | High | 2026-04-16 | 2026-04-21 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0013 | Authentication & Role-Based Access Control | Authentication Flows | Login experience | Implement authSlice (Redux) & session persistence | High | 2026-04-16 | 2026-04-20 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0014 | Authentication & Role-Based Access Control | Authentication Flows | Login experience | Wire login API integration & error handling | High | 2026-04-21 | 2026-04-23 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0015 | Authentication & Role-Based Access Control | Authentication Flows | Registration & account type selection | Build Register page UI | High | 2026-04-22 | 2026-04-27 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0016 | Authentication & Role-Based Access Control | Authentication Flows | Registration & account type selection | Build Account Type Picker (Company / Developer / Guest) | High | 2026-04-14 | 2026-04-16 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0017 | Authentication & Role-Based Access Control | Authentication Flows | Registration & account type selection | Form validation with Zod + React Hook Form | Medium | 2026-04-17 | 2026-04-21 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0018 | Authentication & Role-Based Access Control | Role & Permission Management | Role context & route guards | Build RoleContext & roleContextObject provider | High | 2026-04-24 | 2026-04-28 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0019 | Authentication & Role-Based Access Control | Role & Permission Management | Role context & route guards | Define role catalogue (Guest, Company, Developer, Admin) in roles.ts | High | 2026-04-13 | 2026-04-14 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0020 | Authentication & Role-Based Access Control | Role & Permission Management | Role context & route guards | Implement ProtectedRoute with allow-list guarding | High | 2026-04-29 | 2026-05-01 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0021 | Authentication & Role-Based Access Control | Role & Permission Management | Role context & route guards | Build RoleSwitcher (CRM) for QA/demo impersonation | Low | 2026-04-22 | 2026-04-23 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0022 | Authentication & Role-Based Access Control | Role & Permission Management | Access-denied handling | Build 401 Unauthorized status page | Medium | 2026-04-28 | 2026-04-29 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0023 | Authentication & Role-Based Access Control | Role & Permission Management | Access-denied handling | Build 403 Forbidden status page | Medium | 2026-04-30 | 2026-05-01 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0024 | Public Marketplace Browsing Experience | Home & Site Navigation | Landing page experience | Build Home page hero & featured sections | High | 2026-05-04 | 2026-05-07 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0025 | Public Marketplace Browsing Experience | Home & Site Navigation | Landing page experience | Build sticky header with mega menu navigation | High | 2026-04-24 | 2026-04-29 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0026 | Public Marketplace Browsing Experience | Home & Site Navigation | Landing page experience | Build responsive Sidebar & TopBar shell | Medium | 2026-04-30 | 2026-05-04 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0027 | Public Marketplace Browsing Experience | Home & Site Navigation | Browse & search | Build Browse page with category filters | High | 2026-05-08 | 2026-05-13 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0028 | Public Marketplace Browsing Experience | Home & Site Navigation | Browse & search | Build global SearchBar & Search Results page | High | 2026-05-14 | 2026-05-19 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0029 | Public Marketplace Browsing Experience | Home & Site Navigation | Browse & search | Build Categories index & Category browse pages | Medium | 2026-05-05 | 2026-05-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0030 | Public Marketplace Browsing Experience | Tool & Vendor Detail Pages | Tool detail page | Build Tool Detail page layout & data binding | Medium | 2026-05-20 | 2026-05-22 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0031 | Public Marketplace Browsing Experience | Tool & Vendor Detail Pages | Vendor profile page | Build Vendor Detail page | Medium | 2026-05-25 | 2026-05-27 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0032 | Public Marketplace Browsing Experience | Tool & Vendor Detail Pages | Vendor profile page | Model vendor profile data (vendorProfiles.ts) | Medium | 2026-04-16 | 2026-04-17 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0033 | Public Marketplace Browsing Experience | Gig Marketplace (Buyer-side) | Gig catalogue | Define gig data model (gig.types.ts) & category taxonomy | High | 2026-04-16 | 2026-04-20 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0034 | Public Marketplace Browsing Experience | Gig Marketplace (Buyer-side) | Gig catalogue | Build gigService data-access layer | High | 2026-04-20 | 2026-04-22 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0035 | Public Marketplace Browsing Experience | Gig Marketplace (Buyer-side) | Gig catalogue | Build GigCard & PackageTable components | Medium | 2026-05-11 | 2026-05-13 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0036 | Public Marketplace Browsing Experience | Gig Marketplace (Buyer-side) | Gig details & recommendations | Build Gig Details page | High | 2026-05-28 | 2026-06-02 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0037 | Public Marketplace Browsing Experience | Gig Marketplace (Buyer-side) | Gig details & recommendations | Implement useGig & useRelatedGigs hooks | Medium | 2026-04-23 | 2026-04-27 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0038 | Vendor / Company CRM Workspace | CRM Shell & Navigation | CRM workspace shell | Build CrmProviders, CrmRootLayout & CrmRoute guards | High | 2026-05-04 | 2026-05-07 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0039 | Vendor / Company CRM Workspace | CRM Shell & Navigation | CRM workspace shell | Build CRM Dashboard overview with KPI cards | High | 2026-06-03 | 2026-06-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0040 | Vendor / Company CRM Workspace | Product Management | Product catalogue CRUD | Build Products listing page & ProductTable | High | 2026-05-14 | 2026-05-19 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0041 | Vendor / Company CRM Workspace | Product Management | Product catalogue CRUD | Build ProductFormDrawer (create/edit) | High | 2026-05-20 | 2026-05-22 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0042 | Vendor / Company CRM Workspace | Product Management | Product catalogue CRUD | Build Product Details page | Medium | 2026-06-09 | 2026-06-11 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0043 | Vendor / Company CRM Workspace | Product Management | Product catalogue CRUD | Build ConfirmDialog for destructive actions | Low | 2026-06-12 | 2026-06-15 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0044 | Vendor / Company CRM Workspace | Page & Menu Management | Dynamic page builder | Build Pages Management page & PageConfigDrawer | Medium | 2026-05-25 | 2026-05-28 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0045 | Vendor / Company CRM Workspace | Page & Menu Management | Dynamic page builder | Build Dynamic Page View renderer | Medium | 2026-04-28 | 2026-04-30 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0046 | Vendor / Company CRM Workspace | Page & Menu Management | Navigation menu configuration | Build Menu Management page | Medium | 2026-05-29 | 2026-06-02 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0047 | Vendor / Company CRM Workspace | Page & Menu Management | Navigation menu configuration | Implement menuConfig & useMenuConfig / useVisibleCrmMenu hooks | Medium | 2026-05-01 | 2026-05-05 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0048 | Freelancer (Developer) Workspace | Freelancer Dashboard & Profile | Dashboard overview | Build Freelancer Dashboard with StatCard/StatusPill | High | 2026-06-16 | 2026-06-19 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0049 | Freelancer (Developer) Workspace | Freelancer Dashboard & Profile | Profile management | Build Freelancer Profile page | Medium | 2026-06-22 | 2026-06-24 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0050 | Freelancer (Developer) Workspace | Gigs & Proposals Management | Gig listing management | Build Freelancer Gigs management page | Medium | 2026-06-03 | 2026-06-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0051 | Freelancer (Developer) Workspace | Gigs & Proposals Management | Proposal tracking | Build Freelancer Proposals page | Medium | 2026-06-09 | 2026-06-11 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0052 | Freelancer (Developer) Workspace | Gigs & Proposals Management | Proposal tracking | Wire freelancerSlice (Redux) state | Medium | 2026-05-08 | 2026-05-12 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0053 | Admin Workspace & Governance | Admin Oversight | Admin dashboard | Build Admin Dashboard (platform-wide KPIs) | High | 2026-06-25 | 2026-06-30 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0054 | Admin Workspace & Governance | Admin Oversight | Admin dashboard | Restrict /admin route to Admin role only | High | 2026-05-13 | 2026-05-14 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0055 | Admin Workspace & Governance | Governance & Integrations | Compliance & governance content | Build Governance page | Low | 2026-06-12 | 2026-06-16 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0056 | Admin Workspace & Governance | Governance & Integrations | Compliance & governance content | Build Integrations page | Medium | 2026-06-17 | 2026-06-19 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0057 | User Personalization & Insights | Personal Workspace | Favorites management | Build Favorites page & saved-items state | Medium | 2026-07-01 | 2026-07-03 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0058 | User Personalization & Insights | Personal Workspace | Analytics & reporting | Build Analytics page with Recharts visualizations | Medium | 2026-06-22 | 2026-06-25 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0059 | User Personalization & Insights | Personal Workspace | Account settings | Build Settings page (profile, preferences) | Medium | 2026-07-06 | 2026-07-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0060 | User Personalization & Insights | Personal Workspace | Guest experience | Build Guest Dashboard (limited-access preview) | Medium | 2026-06-26 | 2026-06-30 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0061 | Marketing & Content Pages | Informational Pages | Company information | Build About page | Low | 2026-07-01 | 2026-07-02 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0062 | Marketing & Content Pages | Informational Pages | Company information | Build Contact page | Low | 2026-07-03 | 2026-07-06 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0063 | Marketing & Content Pages | Informational Pages | Commercial & conversion pages | Build Pricing page | Medium | 2026-07-09 | 2026-07-13 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0064 | Marketing & Content Pages | Informational Pages | Commercial & conversion pages | Build Compare page | Low | 2026-07-14 | 2026-07-16 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0065 | Marketing & Content Pages | Informational Pages | Commercial & conversion pages | Build Customers (case studies) page | Low | 2026-07-07 | 2026-07-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0066 | Marketing & Content Pages | Informational Pages | Commercial & conversion pages | Build Documentation page | Low | 2026-05-14 | 2026-05-18 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0067 | Marketing & Content Pages | Informational Pages | Commercial & conversion pages | Build Request Demo page & lead-capture form | Medium | 2026-07-09 | 2026-07-13 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0068 | Quality Assurance & Testing | Test Strategy & Coverage | Functional & regression testing | Define test plan & acceptance criteria per epic | High | 2026-05-20 | 2026-05-22 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0069 | Quality Assurance & Testing | Test Strategy & Coverage | Functional & regression testing | Execute functional test pass — Auth & RBAC | High | 2026-05-25 | 2026-05-27 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0070 | Quality Assurance & Testing | Test Strategy & Coverage | Functional & regression testing | Execute functional test pass — Marketplace & Gigs | High | 2026-05-28 | 2026-06-01 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0071 | Quality Assurance & Testing | Test Strategy & Coverage | Functional & regression testing | Execute functional test pass — CRM & Freelancer workspaces | High | 2026-06-02 | 2026-06-04 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0072 | Quality Assurance & Testing | Test Strategy & Coverage | Cross-browser & responsive QA | Cross-browser compatibility pass | Medium | 2026-06-05 | 2026-06-09 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0073 | Quality Assurance & Testing | Test Strategy & Coverage | Cross-browser & responsive QA | Responsive/mobile layout audit | Medium | 2026-06-10 | 2026-06-12 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0074 | Quality Assurance & Testing | Test Strategy & Coverage | Defect management | Triage & prioritize defect backlog | High | 2026-06-15 | 2026-06-16 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0075 | Quality Assurance & Testing | Test Strategy & Coverage | Defect management | Regression re-test & sign-off for release | High | 2026-06-17 | 2026-06-19 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0076 | DevOps, Deployment & Observability | CI/CD Pipeline | Build & release automation | Configure CI pipeline (lint, type-check, build) | High | 2026-05-26 | 2026-05-28 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0077 | DevOps, Deployment & Observability | CI/CD Pipeline | Build & release automation | Configure environment-based deployment (staging/prod) | High | 2026-05-29 | 2026-06-02 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0078 | DevOps, Deployment & Observability | CI/CD Pipeline | Build & release automation | Set up preview deployments for pull requests | Medium | 2026-06-03 | 2026-06-04 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0079 | DevOps, Deployment & Observability | Monitoring & Observability | Production readiness | Integrate front-end error tracking | Medium | 2026-06-05 | 2026-06-09 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0080 | DevOps, Deployment & Observability | Monitoring & Observability | Production readiness | Set up performance & uptime monitoring | Medium | 2026-06-10 | 2026-06-12 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0081 | Documentation & Project Handover | Technical Documentation | Developer-facing documentation | Write architecture overview & module map | Medium | 2026-06-01 | 2026-06-03 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0082 | Documentation & Project Handover | Technical Documentation | Developer-facing documentation | Document API/service layer contracts | Medium | 2026-06-04 | 2026-06-08 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0083 | Documentation & Project Handover | Technical Documentation | Developer-facing documentation | Write onboarding README & setup guide | Low | 2026-06-09 | 2026-06-10 | 100298
YAM-PJ-0001 | YAKKAY AI Marketplace | YAM-EPI-0084 | Documentation & Project Handover | Technical Documentation | Stakeholder handover | Prepare client walkthrough & release notes | Medium | 2026-06-01 | 2026-06-03 | 100298

## Epic Rollup
Epic Name | Features | Stories | Tasks | Start Date | Due Date
Platform Architecture & Foundation | 2 | 4 | 11
Authentication & Role-Based Access Control | 2 | 4 | 12
Public Marketplace Browsing Experience | 3 | 6 | 14
Vendor / Company CRM Workspace | 3 | 4 | 10
Freelancer (Developer) Workspace | 2 | 4 | 5
Admin Workspace & Governance | 2 | 2 | 4
User Personalization & Insights | 1 | 4 | 4
Marketing & Content Pages | 1 | 2 | 7
Quality Assurance & Testing | 1 | 3 | 8
DevOps, Deployment & Observability | 2 | 2 | 5
Documentation & Project Handover | 1 | 2 | 4